## Sheet1
Decentralized Capital Budget - DCB - 2018
District wise Physical and Financial Progress as at 15th November 2018
Divisional Secretariate Name : Dankotuwa
Division No : 01
S/N | Name of Project | G.N Division |  | Sector | Type of Project | Tot. Est. Cost (Rs.) | Allocation (Rs.) | Expenditure (Rs.) | Unit of Measure | Physical Progress | [10 empty] | No. of Bene | Remarks
|  | Name | No | [6 empty] | * | A | B |  |  |  | C | D | E | F | G | ficiaries
[12 empty] | B1 | B2 | B3 | B4
1 | Reconstruction of Jayasundararama Daham School at Yogiyana | Yogiyana | 459 | SS | Construction | 0 | 100000 | 0 |  |  | 1 | [9 empty] | 250
2 | Connstruction the front gate of Daham School at Jayasundararama temple | Yogiyana | 459 | SS | Construction | 145653.16 | 147750 | 145500 | [11 empty] | 1 | 950
3 | Construction of Daham building for class room at YogiyanaJayasundararamaya | Yogiyana | 459 | SS | Construction | 49780 | 49250 | 48500 | [11 empty] | 1 | 850
4 | Supplying 50 plastic chairs , 15*15 cloth hut and buffet set for Vakada Anyodara Society at Yogiyana | Yogiyana | 459 | SW | Purchase/Grants | 0 | 125000 | 81750 |  |  | 1 | [9 empty] | 250
5 | Contruction of Pre School building at Singakkuliya | Singakkuliya | 460A | SS | Construction | 193953.1 | 200000 | 0 |  |  | 1 | [9 empty] | 315
6 | Molawaththa road in constructionof taood at Lihiriyagama | Lihiriyagama | 462 | RA | Purchase/Grants | 193814 | 197000 | 0 |  |  | 1 | [9 empty] | 550
7 | Supplying 15*15 tent hut for Dinesh Perera Padanama at Lihiriyagama | Lihiriyagama | 462 | SW | Purchase/Grants | 0 | 200000 | 200000 |  |  | 1 | [9 empty] | 150
8 | Supplying 15*10 hut and chairs for Eksath Taruna Sports Society at Lihiriyagama | Lihiriyagama | 462 | SW | Purchase/Grants | 0 | 65000 | 0 |  |  | 1 | [9 empty] | 150
9 | Supplying bufe set for Aruna Priyankara perera Janasahana Padanama at lihiriyagama | Lihiriyagama | 462 | SW | Purchase/Grants | 0 | 50000 | 49750 | [11 empty] | 1 | 345
10 | Supplying 15*10hut for Pragathi Development Society at Mallawa | Mallawa | 463 | SW | Purchase/Grants | 0 | 65000 | 64952 | [11 empty] | 1 | 150
11 | Supplying sound set for Ekamuthu welfair suciaty at malwaththa | Pothuwatawana | 464 | SW | Purchase/Grants | 0 | 0 | 50000 | [11 empty] | 1 | 0
12 | Supplying theBuffet set for Suhada podusewa maranadara Society at Hundirapola | Hundirapola | 464A | SW | Purchase/Grants | 0 | 25000 | 24250 | [11 empty] | 1 | 150
13 | Supplying nescafe machine for suhada maranadhara dociety at Hunadhirapola | Hundirapola | 464A | SW | Purchase/Grants | 0 | 70000 | 62300 | [11 empty] | 1 | 88
14 | Supplying 15*15 tent hut,Bufe set,sound set for prathiba wadihity society at Hundirapola | Hundirapola | 464A | SW | Purchase/Grants | 0 | 150000 | 148943 | [11 empty] | 1 | 378
15 | Supplying 100 Chairs for Suhada maranadara Society at Hundirapola | Hundirapola | 464A | SW | Purchase/Grants | 0 | 100000 | 87300 | [11 empty] | 1 | 125
16 | Supplying Bufe set for apeksha Youth sociaty E/kahatawila | Kahatavila East | 464C | SW | Purchase/Grants | 0 | 50000 | 49750 | [11 empty] | 1 | 0
17 | Supplying still pipes to put white flags for kirimatiyana Eksath Threeweels Society | Kirimetiyana East | 466 | SW | Purchase/Grants | 0 | 15000 | 14700 | [11 empty] | 1 | 285
18 | Supplying 15*10 hut and chairs for Prja miththrathwa padanama at E Kirimatiyana | Kirimetiyana East | 466 | SW | Purchase/Grants | 0 | 65000 | 64952 | [11 empty] | 1 | 150
19 | Construction of Daham pasal buiding for Deeparama Sri Jothirathana at M/kirimatiyana | Mada Kirimetiyana | 466A | SS | Construction | 49978.87 | 49250 | 48500 | [11 empty] | 1 | 380
20 | Constrution of Retaining Wall for Vidhyabandu Piriwena at Kirimatiyana | Temple Junction | 466B | SS | Construction | 193990.98 | 200000 | 0 |  |  | 1 | [9 empty] | 550
21 | Supplying hut for three wheel society at Pansal handiya | Temple Junction | 466B | SW | Purchase/Grants | 0 | 30000 | 0 | [11 empty] | 1 | 120
22 | Supplying 15*15 hut and 53 plastic chairs for Pragathi Wadihity Society | Temple Junction | 466B | SW | Purchase/Grants | 0 | 55000 | 55000 | [11 empty] | 1 | 150
23 | Supplying 15*15 tent hut,100chairs and Bufe set for Sisila Prajamula Society at temple Junction | Temple Junction | 466B | SW | Purchase/Grants | 0 | 250000 | 247200 | [11 empty] | 1 | 250
24 | Supplying road lamps for Wennappuwa Pradeshiya saba to put road lamps in Bothalegama Gs divition | Bothalegama | 466C | REL | Purchase/Grants | 0 | 20000 | 0 | [10 empty] | 1 |  | 875
25 | Supplying 15*15 tent hut ,50 chairs, and Sound set,plastic water tank,sodium flasher for Nagena Tharu sports society at Bothalegama | Bothalegama | 466C | SW | Purchase/Grants | 0 | 250000 | 249221 | [11 empty] | 1 | 378
26 | Supplying water for Molewaththa house schene at Kirimatiyana | Kirimetiyana West | 466F | SW | Purchase/Grants | 0 | 48875 | 48875 | [11 empty] | 1 | 150
27 | Preparation of entrance at Haldaduwana Pushparamaya | Haldanduwana South | 468A | REC | Construction | 291097.79 | 300000 | 291122.79 | [11 empty] | 1 | 550
28 | Supplying 15*10 hut and Chairs for Isuru Development Society at M/ Haldaduwana | Mada Haldanduwana | 468B | SW | Purchase/Grants | 0 | 65000 | 64800 | [11 empty] | 1 | 150
29 | Supplying 02 VIP hut for Moyrigin Osjen Muslim Church at madikale | Pahala Bujjampola | 470 | SW | Purchase/Grants | 88000 | 70000 | 0 |  |  | 1 | [9 empty] | 0
30 | Close the work of Siriwimala Dharmayathanaya at Bothalegama | Ihala Bujjampola | 470A | SW | Construction | 0 | 250000 | 0 |  |  | 1 | [9 empty] | 1000
31 | Supplying VIP hut for Bodhiyapura Udara sports club Bujjampola | Ihala Bujjampola | 470A | SW | Purchase/Grants | 0 | 0 | 0 | [5 empty] | 1 | [6 empty] | 0
32 | Supplying 01 VIP hut for Musjindul Mohowar Muslim Church at Madikale | Ihala Bujjampola | 470A | SW | Purchase/Grants | 0 | 35000 | 31000 | [11 empty] | 1 | 124
33 | Supplying 15*15 tent hut for Shakthi Maranadara Society at N/Atiyawala | Atiyawala North | 471 | SW | Purchase/Grants | 0 | 55000 | 55000 | [11 empty] | 1 | 110
34 | Supplying 15*10 hut and chairs for Diriya Anyodara Socieety at S/Atiyawala | Atiyawala South | 471A | SW | Purchase/Grants | 0 | 65000 | 64800 | [11 empty] | 1 | 142
35 | Supplying chairs for Ekamuthu Anyodara Society at S /Atiyaala | Atiyawala South | 471A | SW | Purchase/Grants | 0 | 25000 | 24444 | [11 empty] | 1 | 150
36 | Supplying chairs for Nawodini Grama Shakthi Deewara woman Society at Atiyawala South | Atiyawala South | 471A | SW | Purchase/Grants | 0 | 25000 | 24444 |  |  | 1 | [9 empty] | 150
37 | Constraction of Karanwaththa temple | Motamulla | 471B | CD | Construction | 96662.49 | 98500 | 96662 | [11 empty] | 1 | 0
38 | Construction of Daham building at Karanawaththa temple | Motamulla | 471B | SS | Construction | 0 | 200000 | 0 |  |  | 1 | [9 empty] | 450
39 | Complete the balance work of Comminity hall at Matikotuwa | Metikotuwa | 472 | SS | Construction | 0 | 300000 | 0 | [11 empty] | 1 | 485
40 | Complete the balance work of Daham Pasal building at Thamarakuliya temple | Thamarakuliya | 472A | SS | Construction | 193998 | 200000 | 193998 | [11 empty] | 1 | 850
41 | Supplying 15*10 hut and Chairs for senth Japamala sports Society at Godalla | Godalla | 473 | SW | Purchase/Grants | 0 | 65000 | 64952 | [11 empty] | 1 | 450
42 | Construction of Godalla Church | Godalla | 473 | SW | Purchase/Grants | 290748.5 | 300000 | 290748 | [11 empty] | 1 | 450
43 | Supplying 15*20 hut and chairs for Sumithuru Sports society at Morukkuliya | Morukkuliya | 473A | SW | Purchase/Grants | 0 | 65000 | 0 | [6 empty] | 1 | [5 empty] | 116
44 | Supplying Chairs for Gothami Wadihity Society at Morukkuliya | Morukkuliya | 473A | SW | Purchase/Grants | 0 | 50000 | 49761 | [11 empty] | 1 | 150
45 | Supplying chairs for Eksath Awamanglyadara and Welwair Society at Morukkuliya | Morukkuliya | 473A | SW | Purchase/Grants | 0 | 50000 | 49761 | [11 empty] | 1 | 150
46 | Supplying Chairs, hut, sports Instrument ,cabed, saspane,flash light for registation Society | Dankotuwa South | 474A | SW | Purchase/Grants | 0 | 500000 | 210000 | [11 empty] | 1 | 450
47 | Supplying Instrument for registered Society at Dankotuwa Divition | Dankotuwa South | 474A | SW | Purchase/Grants | 0 | 200000 | 0 |  |  | 1 | [9 empty] | 150
48 | Cnstraction of Dahampasal building for buddhist atE/Dankotuwa | Dankotuwa East | 474B | CD | Construction | 250000 | 250000 | 0 |  |  | 1 | [9 empty] | 250
49 | Complete the balance work of libary building in darma pradepa budhist Centre at E/Dankotuwa | Dankotuwa East | 474B | SS | Construction | 0 | 300000 | 300000 | [11 empty] | 1 | 800
50 | Supplying Western band musical instruments for Dankotuwa B/M/V | Dankotuwa East | 474B | SS | Purchase/Grants | 0 | 100000 | 95800 | [11 empty] | 1 | 600
51 | Supplying 15*10 hut and chairs for welfaire Society at E/Dankotuwa | Dankotuwa East | 474B | SW | Purchase/Grants | 0 | 65000 | 0 |  |  | 1 | [9 empty] | 345
52 | provision of driving licences to low income persons in Dankotuwa division | Dankotuwa East | 474B | SW | Purchase/Grants | 0 | 84000 | 0 |  |  | 1 | [9 empty] | 7
53 | Supplying 10*10 hut for Samagi Awamanglyadara Society at E/Dankotuwa | Dankotuwa East | 474B | SW | Purchase/Grants | 0 | 50000 | 50000 | [11 empty] | 1 | 150
54 | Supplying sports Instrument for registation Society at Dankotuwa Divition | Dankotuwa East | 474B | SW | Purchase/Grants | 0 | 61125 | 0 |  |  | 1 | [9 empty] | 345
55 | Apling Tilei for Madikale Dewasthanaya at W/Dankotuwa | Dankotuwa west | 474C | SS | Construction | 0 | 200000 | 193966.5 | [11 empty] | 1 | 355
56 | Supplying 15*10 hut and Chairs for Welfaire Society at Katakalagaha waththa | Pahala Dummalakotuwa | 474E | SW | Purchase/Grants | 0 | 65000 | 64952 | [11 empty] | 1 | 114
57 | Repair the Stage of consert hall in Don Bosko Seminary in Katukenda East | Katukenda East | 475 | SS | Construction | 0 | 200000 | 0 |  |  | 1 | [9 empty] | 1500
58 | Supplying 25 plastic chairs for Maranadara Society at Katukenda East | Katukenda East | 475 | SS | Purchase/Grants | 0 | 25000 | 21825 | [11 empty] | 1 | 450
59 | Supplying Chairs for Sri Abesinharamaya Eksath Yan budhist Society at Katukenda East | Katukenda East | 475 | SW | Purchase/Grants | 0 | 50000 | 49920 | [11 empty] | 1 | 150
60 | Supplying chairs for Sangabodhi Viduhala at Katukenda | Katukenda East | 475 | SW | Purchase/Grants | 0 | 50000 | 49761 | [11 empty] | 1 | 900
61 | Balance work and of Cemetry in Katukenda west | Katukenda west | 475A | REC | Construction | 92432.6 | 98500 | 92432 | [11 empty] | 1 | 650
62 | Supplying plastic chairs for Vasana Sports Society at mada Katukenda | Katukenda west | 475A | SW | Purchase/Grants | 0 | 25000 | 21825 |  |  | 1 | [9 empty] | 88
63 | Supplying plastic chairs for Grama sanwardana Society at Katukenda west | Katukenda west | 475A | SW | Purchase/Grants | 0 | 25000 | 21825 |  |  | 1 | [9 empty] | 150
64 | Supply 15*10 hut and chairs for olders society at w/katukenda | Katukenda west | 475A | SW | Purchase/Grants | 0 | 65000 | 64952 | [11 empty] | 1 | 125
65 | Supplying15*10 hut for Sister Helena awamanglyadara Society at W/katukenda | Katukenda west | 475A | SW | Purchase/Grants | 0 | 65000 | 0 |  |  | 1 | [9 empty] | 124
66 | Supplying 15*10 hut and Chairs for Development Society at S/Gonawila | Gonavila South | 477A | SW | Purchase/Grants | 0 | 65000 | 64952 | [11 empty] | 1 | 135
67 | Supplying water pump for farmers society at Gonawila maha wel yaya | Mada Gonavila | 477B | SW | Purchase/Grants | 0 | 70000 | 0 |  |  | 1 | [9 empty] | 200
68 | Supplying a Chairs for Wadihity purawasi Society at Mada Gonawila | Mada Gonavila | 477B | SW | Purchase/Grants | 0 | 40000 | 39285 | [11 empty] | 1 | 150
[6 empty] | 2130109.49 | 7449250 | 4384431.29 |  | 0 | 21 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 44 | 21654