## Sheet1
Rapid Rural Development Program (RRDP) Gamperaliya - 2018
District wise Physical and Financial Progress as at 15th November 2018
Divisional Secretariate Name : Dankotuwa
Division No : 01
S/N | Name of Project | G.N Division |  | Sector | Type of Project | Tot. Est. Cost (Rs.) | Allocation (Rs.) | Expenditure (Rs.) | Unit of Measure | Physical Progress | [10 empty] | No. of Bene | Remarks
|  | Name | No | [6 empty] | * | A | B |  |  |  | C | D | E | F | G | ficiaries
[12 empty] | B1 | B2 | B3 | B4
1 | Renovation the transformer waththa road at Sendiriyamulla | Sendiriyamulla | 461 | RA | Construction | 916377.3 | 1000000 | 406736 | [9 empty] | 1 |  |  | 750
2 | Renovation the Koshena North janapada road | Mallawa | 463 | RA | Construction | 970247.6 | 1000000 | 780506.7 | [9 empty] | 1 |  |  | 900
3 | Development of Suvusudhdharama temple at Mallawa | Mallawa | 463 | SS | Construction | 485345.34 | 500000 | 0 | [9 empty] | 1 |  |  | 1000
4 | Reconstruction of St. Anthony's church at Mallawa | Mallawa | 463 | SW | Construction | 485301.66 | 500000 | 0 | [11 empty] | 1 | 800
5 | Construction of toilet block at Mallawa school | Mallawa | 463 | SW | Construction | 999752.27 | 1000000 | 0 | [7 empty] | 1 |  |  |  |  | 1000
6 | Development of maha viharaya Pothuwatawana | Pothuwatawana | 464 | SS | Construction | 485326.94 | 500000 | 0 | [8 empty] | 1 |  |  |  | 1000
7 | Reconstruction of Kahatawila church | Pothuwatawana | 464 | SW | Construction | 485415.86 | 500000 | 0 | [7 empty] | 1 |  |  |  |  | 600
8 | Construction of sportd pavilian at Pothuwatawana School | Pothuwatawana | 464 | SW | Construction | 999175.5 | 1000000 | 0 | [7 empty] | 1 |  |  |  |  | 1500
9 | Development of Kshethrarama temple at Kahatavila | Kahatavila West | 464B | SS | Construction | 485297.57 | 500000 | 0 | [7 empty] | 1 |  |  |  |  | 1000
10 | Renovation the front road of Abhinawaramaya at Thulawala | Thulawala | 465 | RA | Construction | 738460.2 | 1000000 | 0 | [9 empty] | 1 |  |  | 800
11 | Development the Nagawanarama temple at Thulawala | Thulawala | 465 | SS | Construction | 485432.38 | 500000 | 0 | [9 empty] | 1 |  |  | 1000
12 | Renovation the road near Kirimatiyana Buddhist girls college | Kirimetiyana East | 466 | SS | Construction | 970645.4 | 1000000 | 739012.7 | [11 empty] | 1 | 1000
13 | Development of playground at Kirimatiyana girls college | Kirimetiyana East | 466 | SS | Construction | 0 | 1000000 | 0 | [8 empty] | 1 |  |  |  | 1500
14 | Reconstruction of st.Jerad church at Kirimetiyana | Kirimetiyana East | 466 | SW | Construction | 0 | 500000 | 0 |  |  | 1 | [9 empty] | 800
15 | Development of Pushparama temple at Haldanduwana | Mada Haldanduwana | 468B | SW | Construction | 0 | 500000 | 0 | [12 empty] | 1000
16 | Development of Seelarathana Buddhist center at Ihala Mohottimulla | Ihala Mohottimulla | 469 | SS | Construction | 485382.1 | 500000 | 0 | [7 empty] | 1 |  |  |  |  | 1000
17 | Renovation of Hettiwaththa road at Mohottimulla | Pahala Mohottimulla | 469A | RA | Construction | 526745.2 | 1000000 | 406835.8 | [9 empty] | 1 |  |  | 600
18 | Renovation of Nelum Uyana athuru margaya at Metikotuwa | Metikotuwa | 472 | RA | Construction | 895576.12 | 1000000 | 692382.46 | [10 empty] | 1 |  | 850
19 | Reconstruction of Thamarakuliya temple | Thamarakuliya | 472A | SW | Construction | 485431.84 | 500000 | 0 | [7 empty] | 1 |  |  |  |  | 1000
20 | Renovation the road Ranpiyagama to samupakara junction | Godalla | 473 | RA | Construction | 970736.3 | 1000000 | 744333.8 | [10 empty] | 1 |  | 700
21 | Development of Godalla church | Godalla | 473 | SS | Construction | 485337.85 | 500000 | 479189 | [11 empty] | 1 | 1000
22 | Construction of toilet block at Godalla school | Godalla | 473 | SS | Construction | 970527.57 | 1000000 | 0 | [7 empty] | 1 |  |  |  |  | 2000
23 | Renovation Church roads at Morukkuliya | Morukkuliya | 473A | RA | Construction | 970792.01 | 1000000 | 0 | [9 empty] | 1 |  |  | 700
24 | Reconstruction of Morukkuliya Church | Morukkuliya | 473A | SS | Construction | 484686.41 | 500000 | 0 | [11 empty] | 1 | 1000
25 | Reconstruction of vishnu Katharagama Devalaya at Morukkuliya | Morukkuliya | 473A | SW | Construction | 485410.66 | 500000 | 0 | [9 empty] | 1 |  |  | 600
26 | Construction of toilet system at Dankotuwa girls college at Dankotuwa south | Dankotuwa South | 474A | SS | Construction | 970527.57 | 1000000 | 0 | [11 empty] | 1 | 2000
27 | Reconstruction the Madikele church | Dankotuwa west | 474C | SS | Construction | 484999.5 | 500000 | 478999.5 | [11 empty] | 1 | 1000
28 | Renovation the Gurugewatta 1 road at Dummalakotuwa | Pahala Dummalakotuwa | 474E | RA | Construction | 682895 | 1000000 | 530502.4 | [10 empty] | 1 |  | 700
29 | Development of Munigunarama temple at Katukenda west | Katukenda west | 475A | SS | Construction | 485146.27 | 500000 | 310258.51 | [8 empty] | 1 |  |  |  | 1000
[6 empty] | 17890972.42 | 21500000 | 5568756.87 |  | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 3 | 8 | 3 | 6 | 28800